## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | DAYS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Add Item to Seller/ View Merchant Profile | 1 | 4 | 1 | 2 | 100%
Add pictures for item | 2 | 4 | 2 | 2 | 100%
Find Items | 3 | 2 | 2 | 2 | 100%
Add to Cart | 5 | 4 | 5 | 5 | 100%
Create Merchant Account | 8 | 1 | 8 | 1 | 100%
Edit/view Customer Profile | 4 | 3 | 4 | 6 | 100%
Delete Customer Account | 5 | 4 | 5 | 3 | 100%
Create Customer Account | 5 | 2 | 5 | 5 | 100%
Login/Logout for customers | 5 | 2 | 5 | 6 | 100%
Login/Logout for Merchant | 8 | 1 | 8 | 1 | 100%
Add Product Rating | 6 | 1 | 5 | 8 | 100%
Splash Page | 9 | 3 | 9 | 4 | 100%
Buy Item | 9 | 5 | 9 | 2 | 100%
UI Interactive Support | 9 | 7 | 9 | 7 | 100%
View all listed items | 5 | 2 | 5 | 2 | 100%
Biddable Items | 11 | 7 | 11 | 10 | 35%